## TimeLine
Aquaria Morocco Data Analysis Project
Timeline
Phase | Task | Duration | Start Date | End Date
Phase 1: Planning | Define research questions, finalize scope | 1 week | Aug 11, 2025 | Aug 17, 2025
Phase 2: Data Collection | Conduct surveys, interviews, and secondary research | 3 weeks | Aug 18, 2025 | 07-sept.-25
Phase 3: Data Analysis | Analyze water demand, competition, and regulations | 3 weeks | 08-sept.-25 | 28-sept.-25
Phase 4: Report Development | Draft report and presentation | 2 weeks | 29-sept.-25 | 12-oct.-25
Phase 5: Review and Finalization | Incorporate feedback, finalize deliverables | 1 week | 13-oct.-25 | 19-oct.-25
Phase 6: Presentation | Present to Aquaria’s management | 1 day | 20-oct.-25 | 20-oct.-25
Total Duration: 10 weeks